TERMS OF REFERENCE

for

Data Center Expansion Support

# Background Information

Digitalization is increasingly becoming the backbone of any and all functional restructuring in the public sector, an objective driver of change management and a precondition for transformative development. Going digital, being a horizontal measure, is also accelerating the attainment of Sustainable Development Goals (in further text: SDG). While it directly falls under SDG 16, e-Governance is contributing to building stronger institutions – effective, accountable and transparent – at all levels.

The Government of Serbia (GoS), elected in June 2017, has prioritized the digital transformation of the national economy and state administration. The Prime Minister's Keynote Address at the Parliament stressed digitalization and education as the most important catalysts of innovations, competitiveness and growth for Serbia in the coming years. It also stressed the need for a rapid digitalization of public administration and provision of integrated, secure and citizen-focused electronic services. This political support materialized in August 2017, when the new Government formed the Office for IT and e-Government (OITeG) and appointed the Prime Minister as head of the Council for Innovative Entrepreneurship and Information Technologies (IT Council).

In addition, the Government of Serbia has requested assistance from the World Bank in supporting the reform efforts, through a loan. To this effect, the World Bank has initiated the Enabling Digital Governance Project (EDGE). The Project, launched back in April 2019, and restructured in June 2024, aims at contributing to development of the digitalization in Serbia, through implementation of the following components:

Component 1: Foundations for Digital Service Delivery

The objective of this component is to establish the necessary cross-cutting foundations to support the use of ICTs in the provision of public services to citizens, and businesses, including inter alia, regulations, standards, and digital infrastructure.

Component 2. Citizen-Centric Digital Services

The objective of this component is to support the three dimensions of project objectives—access, quality, and efficiency of e-services: (a) integrate change management and citizen engagement activities into this digital transformation process; (b) strengthen the institutional capacity of the OITeG and other key stakeholders for leading and coordinating intergovernmental activities in an agile, user-centric way; and (c) streamline the implementation arrangements through a partnership between OITeG and Public Policy Secretariat (PPS) of the Prime Minister’s office.

Component 3. Digital Skills Development and Project Management

This component focuses on the integration of change management, communication, and citizen feedback into Component 2.

For the purposes of effectively managing and coordinating EDGE and future Projects with International Financial Institutions (IFI) financing, the Project Implementation Unit (PIU) has been founded at the OITeG.

Within this EDGE program context, the Government now seeks specialized support to secure continuity of certification, plan capacity expansion, and modernize existing facilities in line with EU-aligned standards.

Serbia's digital transformation relies on robust, sovereign data-center capacity to host critical public­ sector workloads. The Government Data Center in Kragujevac has been a flagship success­ independently certified to EN 50600 Class 4 (highest availability class) in 2023, a distinction noted as the first of its kind in Eastern/Southeastern Europe and underscoring the facility's reliability and operational maturity.

As part of normal lifecycle management, the current EN 50600 certificate reaches expiry in March 2026, making continuity of certification essential to avoid any gap in verified compliance and to maintain confidence for sensitive government workloads.

Looking ahead, sustained growth in e-government services and compute demand raises strategic questions about geographic capacity and resilience. In addition to maintaining certification at Kragujevac, the Government is assessing options to expand beyond Kragujevac, including potential sites in cities such as Nis, Novi Sad, or others and to evaluate refurbishment/modernization of the TKC facility in Belgrade to determine its suitability for hosting workloads alongside the national platform.

# Objectives

Select a multidisciplinary consultant to (I) secure EN 50600 recertification for the Government Data Center in Kragujevac before the March 2026 expiry, (2) deliver a decision-ready data center expansion strategy with a recommended new site in Serbia, and (3) provide a modernization roadmap for the TKC facility in Belgrade to increase government data center capacity and extend asset life.

# Scope and Phases

## Re-Certification (EN50600) - Support the renewal of the Data Center in Kragujevac certification before the March 2026 deadline to ensure continued compliance. This will include:

Managing the re-certification process

Preparing and reviewing required compliance documentation

Coordinating with certification bodies and facilitating timely finalization of the recertification process

## Data Center Expansion Strategy – Provide a structured approach for selecting a potential new site location for expansion of the governmental Data Center in Kragujevac (e.g., Ni, Novi Sad, or other). This will include:

Reviewing available land plots

Shortlisting viable sites, validate and evaluate across the critical parameters including risk analyses and mitigation assessment

Considering infrastructure and energy availability

Analyze potential technology options (containers, brick & mortar) and give recommendation

Comparing options and providing recommendations, including high level timeline and budget estimation

## TKC DC Expansion & Modernization Options – Evaluate opportunities to refurbish or upgrade the TKC into DC facility (part of the floors 5, 7, 8) in order to accommodate future clients, increase capacity, and extend the site's operational lifecycle. This will include:

A feasibility assessment covering power availability, reliability, security, and other factors required to meet prospective tenant standards

Development of high-level technical design scenarios, including checking the feasibility of potential redundancy configurations and security zone concepts

Preparation of a high-level timeline and cost estimate for implementation

# Timeframe and duration

The Consultant shall provide services under lump sum Contract paid upon acceptance of deliverables. The Consultant shall perform the Services over 4 (four) months, approximately.

# Deliverables

| # | Description | Deadline |
| --- | --- | --- |
| 1 | Expansion feasibility & site shortlist Concise feasibility study with a shortlist of viable locations in Serbia (e.g., Ni, Novi Sad, others) and key constraints/risks | 4 (four) weeks after contract signing |
| 2 | EN 50600 Re-certification Evidence Pack submitted Complete, up-to-date documentation prepared and submitted to the certification body | 4 (four) weeks after contract signing |
| 3 | TKC modernization feasibility & roadmap Focused feasibility assessment for TKC (selected areas of floors 5, 7, 8) with options and a high-level implementation plan/capex range. | 6 (six) weeks after contract signing |
| 4 | Preferred site recommendation (decision brief) Clear recommendation of one preferred site with high-level schedule and weeks after budget to enable a go/no-go decision. | 8 (eight) weeks contract signing |
| 5 | Support during and until completion of EN 50600 re-certification | 16 (sixteen) weeks after contract signing |

# Consultant Qualifications

At least one (1) completed EN 50600 Data Center certification engagement in the last seven (7) years (including coordination with a certification body and documentation pack preparation for example risk analysis).

Proven experience on minimum five (5) data center strategy/ feasibility/ due diligence projects of similar complexity with energy needs of more than 2 MW, completed in the last seven (7) years.

Proven experience in at least one (1) Data Center project strategy, operational and business model or similar projects for Oat Centers in accordance with Standard EN50600

Experience in consulting projects related to data center with power higher than 30 MW is an advantage

Experience with minimum 2 projects related to HPC such as strategy, due diligence or operational projects related to HPC or Al-oriented data centers, HPC as a Service monetization or operation projects, etc.

Demonstrated experience with minimum 2 public-sector data center projects is advantageous

# Team and Technical requirements

The Team should consist at minimum of:

## Team Leader

Graduate degree in IT, ICT, business administration or similar fields; post graduate degree would be an asset.

At least seven (7) years of experience on project management positions.

Relevant experience in large-scale ICT project delivery.

Experience as Team Leader/Project Manager in at least one (1) project for data center with energy needs of more than 2 MW.

Fluency in English, both written and spoken.

## Business Consultant(s) (at least 2 experts out of which one should possess at minimum)

Graduate degree in law, finance, business administration, IT, or similar fields;

At least four (4) years of experience on consulting and project management positions in large-scale projects.

Experience in minimum 5 projects related to Data Center market analysis and related business model definition including go to market for data center with energy needs of more than 2 MW

Experience in consulting projects such as due diligence, strategy, market assessment for Data Centers with energy needs of more than 30 MW is an advantage

Experience in data center site evaluation is an advantage

Direct experience with data center EN50600 certification process is an advantage

Fluency in English, both written and spoken. Fluency in Serbian would be an advantage.

## DC Specialist

Graduate degree in IT, ICT, or similar fields.

At least seven (7) years of experience in designing/operating large-scale data centers.

Participated in designing, preparing feasibility studies or certification projects for at least two data centers with energy needs of more than 2 MW, in the past seven years.

Experience in at least one (1) Data Center project (ongoing or finished) designed in accordance with Standard EN50600;

Experience with standards related to design, construction, equipping and operation of data centers will be considered and advantage.

Experience in data center site evaluation is an advantage.

Direct experience with data center EN50600 certification process is an advantage.

Fluency in English, both written and spoken. Fluency in local language would be an advantage.

## Business Analyst(s) (at least 2 experts out of which one should possess at minimum)

Graduate degree in law, finance, business administration, IT, or similar fields.

Experience in minimum 2 projects related to Data Center market analysis and related business model definition including go to market for data center with energy needs of more than 2 MW.

Experience in minimum one (1) consulting projects related to due diligence, strategy or market.

Experience in at least one (1) AI project (Use cases or governance model analysis).

Fluency in English, both written and spoken. Fluency in local language would be an advantage.

# Evaluation

The Consultant which obtains the highest score during evaluation of expressions of interest will be invited to submit technical and financial proposals.